## Project Plan
Date | Activity | Notes
2013-01-15 | Create newsletter (I recommend Mailchimp) | It is often a good idea to have a free something for download as an enticer for people to sign up. Doesn't need to be much, could be a gluten free basic panty list? All the items you want to have on hand so you can make standard recipes gluten free?
2013-01-16 | Analyse and examine keyword ideas to help you come up with a title
2013-01-17 | Decide what you want from product | Eg are you just testing the waters with a low price smaller product at around $4.95 or more complex product at $19.95. This will be very much determined by how much time you have to spend on the product. For a first time product, perhaps going smaller first to see how it works will be the best option.
2013-01-18 | Do further idea and key word analysis | Look in your niche and see if your product ideas is already out there. This doesn't mean it can't be done, but it means you will need to find your own unique angle.
2013-01-21 | Launch newsletter in a post on a high traffic day on the blog | Explain its frequency and purpose. Eg will offer additional info to the blog posts and news on products etc. Add sign up code from Mailchimp to a prominent place on the blog.
2013-01-23 | Document plan for content | Best to have an outline of your e-product that you can work too. The product can include bulk of content from blog, but will need some extras to make it worth while buying.
2013-01-25 | Create promotion plan | Eg guest posting on other blogs, link ups, articles for other sites, etc. Email friends and ask for support with facebook shout outs etc
2013-01-26 | Determine format for e-book | Portrait / landscape. template design, header, font, spacing, headings h1, h2, h3 etc - needed to be able to create a table of contents
2013-02-01 | Collate and create the content for the e-book in word
2013-02-08 | Edit the content of the book
2013-02-13 | Create a social media promotion plan for the e-book
2013-02-15 | Finalise format of the content
2013-02-16 | Write content for guest posts
2013-02-17 | Have content proof read and sent back to you by this date
2013-02-18 | Work on content for launch newsletter
2013-02-19 | Final changes to document
2013-02-20 | Convert to pdf and create image for e-book
2013-02-21 | Send out newsletter with original content and promo for product
2013-02-22 | Write content for launch on newsletter and blog
2013-02-23 | Sign up with e-junkie and upload product | Create a paypal account if you don't already have one. Decide if you are going to do affiliates or not.
2013-02-24 | Write content for guest posts
2013-02-25 | Write content for guest posts
2013-02-26 | Finalise content for newsletter launch
2013-02-27 | Finalise content for launch post for the blog
2013-02-28 | Launch product on blog and newsletter
2013-03-01 | Add a banner advertisement for the e-book on all relevant pages on the blog | See this page on my blog for my parties with kids e-book http://planningwithkids.com/2008/08/21/tea-cup-biscuits/
Formulas:
Date = [Date, row above]+1